## Excel Gantt Chart Template
Excel Gantt Chart Template |  |  |  | Current Date
Enter Your Project Details Here |  |  | DURATION (days)
START DATE | END DATE | DESCRIPTION
2020-09-27 | 2020-10-09 | Problem Definition | 12
2020-10-09 | 2020-10-16 | Feasibility Analysis | 7
2020-10-16 | 2020-10-30 | User Requirement Analysis | 14
2020-11-19 | 2020-11-27 | Designing Data Flow | 8
2020-11-27 | 2020-12-04 | ERD and Project Scheduling | 7
2020-12-04 | 2020-12-11 | Designing UML Diagrams | 7
2020-12-11 | 2020-12-18 | Prototyping | 7
2020-12-18 | 2021-01-01 | Development | 13
2021-01-01 | 2021-01-08 | Testing and Debugging | 7